## Accessibility Bugs 1st Round
ID | Work Item Type | Title | State | Assigned To | Aprobado por Accessibility | Responsable | Status (Completado/En progreso/ No comenzado) | Tags | Comentarios | Severity | ADO Synced | ADO State | ADO Assigned to
1516891 | Bug | Bug 1516891: [Screen Readers - OLP Power Apps - Landing page]: Heading structure is not correctly defined on the page. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado |  | El deployment pasado no migró la aplicación con los bugs resueltos. | 2 - High | #REF! | #REF! | #REF!
1516910 | Bug | Bug 1516910: [Visual Requirement - OLP Power Apps - Landing page]: Luminosity contrast ratio for the focus indicator on the 'Let's start' button is less than 3:1. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.11; NewBaselineAssessment; RecID_8303 | El deployment pasado no migró la aplicación con los bugs resueltos. WP (12/09/22): Revisar, se arrgeló y se verificó en UAT el viernes. | 3 - Medium | #REF! | #REF! | #REF! | Si
1516917 | Bug | Bug 1516917: [Supporting the platform - OLP Power Apps - Landing page]: After resizing the page at 200% zoom, page content is not displaying properly. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.4; NewBaselineAssessment; RecID_8303 | Ajustamos los elementos del encabezado cumpliendo con los dos escenarios de zoom, nombre visible y foto visible en pantalla de portatil no de monitor | 3 - Medium | #REF! | #REF! | #REF! | Reactivado
1517380 | Bug | Bug 1517380: [Supporting the platform - OLP Power Apps - Landing page]: After resizing the page at 400% zoom mode, Keyboard Focus indicator is not properly visible for 'play video' button, while navigating using tab/shift tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF! | No revisado
1517386 | Bug | Bug 1517380: [Supporting the platform - OLP Power Apps - Landing page]: After resizing the page at 400% zoom mode, Keyboard Focus indicator is not properly visible for 'play video' button, while navigating using tab/shift tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.3; NewBaselineAssessment; RecID_8303 | Discutir solución con Federico, Focus se hizo sobre otro elemento. | 3 - Medium | #REF! | #REF! | #REF! | Pending w/ dependecy
1517602 | Bug | Bug 1517602: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus indicator is overlying on controls present inside the filter control. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.7; NewBaselineAssessment; RecID_8303 |  | 4 - Low | #REF! | #REF! | #REF!
1517603 | Bug | Bug 1517603: [Visual Requirements - OLP Power Apps - Content page]: Luminosity contrast ratio of focus indicator for 'apply' and 'clear all' buttons is 2.1:1 which is less than 3:1. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yAuto; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; K4W; MAS 1.4.11; NewBaselineAssessment; RecID_8303 | Para este bug se debe trabajar con el Software Colour Contrast Analyser. Link para descargar software: https://www.tpgi.com/color-contrast-checker/ | 2 - High | #REF! | #REF! | #REF!
1517604 | Bug | Bug 1517604: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus is not moving to controls of filter dropdown when we invoke it. | New | William Pena <v-wpena@ .com> | Pending w/ dependecy | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.3; NewBaselineAssessment; RecID_8303 | Accessibility team nos confirmó que es un product related bug. | 2 - High | #REF! | #REF! | #REF!
1517605 | Bug | Bug 1517605: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard tab focus loss is observed after invoking 'Skip to main content'. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.3; NewBaselineAssessment; RecID_8303 | Comentar en ADO: El comando de "Skip to ,ain Content" no es un control que nosotros configuremos, es algo del producto. | 4 - Low | #REF! | #REF! | #REF!
1517616 | Bug | Bug 1517616: [Screen Readers - OLP Power Apps - Content page]: Navigation and search landmarks/regions are not defined in the page. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Comentar en ADO con links de PA limitations. | 3 - Medium | #REF! | #REF! | #REF!
1517619 | Bug | Bug 1517619: [Screen Readers - OLP Power Apps - Content page]: Headings are not defined in the page while navigating using heading shortcut key 'H' or down arrow key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.6; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517628 | Bug | Bug 1517628: [Visual Requirement - OLP Power Apps - Content page]: After applying text spacing, the page content in the page is not properly displaying. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.12; NewBaselineAssessment; RecID_8303 | Preguntamos por herramienta de text spacing. Después de una reunión con el dos ingenieros de Accessibility, Dipankar y Sudheer. Nos comentaron que si utilizamos la fuente Segoe UI, no deberiamos de tener problema con el tema de text spacing. | 3 - Medium | #REF! | #REF! | #REF!
1517633 | Bug | Bug 1517633: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus indicator is overlying with control while navigating using tab or shift tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.7; NewBaselineAssessment; RecID_8303 | Este punto no tiene que ver con PowerApps sino con el navegador Edge o Chrome. | 4 - Low | #REF! | #REF! | #REF!
1517638 | Bug | Bug 1517638: [Screen Readers - OLP Power Apps - Content page]: Screen Readers (NVDA/JAWS) are narrating incorrect name for logo as 'organizational logo' in the page, while navigating using Browse/VPC mode. | Pending w/ dependency | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | No tiene nada que ver con la canvas app. | 3 - Medium | #REF! | #REF! | #REF!
1517691 | Bug | Bug 1517691: [Usable - OLP Power Apps - Content page]: 'Collapse All' button is visually appearing as normal text. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMASP3; A11yUsable; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; NewBaselineAssessment; RecID_8303 | Completado, con Borde y Focus Border funcional para navegación con teclado. Funcional igual para Aquatic y Desert themes. | 3 - Medium | #REF! | #REF! | #REF!
1517727 | Bug | Bug 1517727: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus is unnecessarily moving to whole tile section upon activating 'Collapse All' or 'Expand All' control. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.3; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517736 | Bug | Bug 1517736: [Keyboard Navigation - OLP Power Apps - Content page]: Filter control is not getting closed via ‘ESC’ key. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.5; NewBaselineAssessment; RecID_8303 | Revisar si es PowerApps dependency, ya que no se ha encontrado una función que implemente lo que el usuario oprima en el teclado. | 4 - Low | #REF! | #REF! | #REF!
1517884 | Bug | Bug 1517884: [Screen Readers - OLP Power Apps - Content page]: Screen readers focus is not in sequential order on the page while navigating using arrow keys in browse/VPC mode. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.2.10; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517891 | Bug | Bug 1517891: [Screen Readers - OLP Power Apps - Content page]: Ensures every form element has a label. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yAuto; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; K4W; MAS 4.1.2; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517896 | Bug | Bug 1517896: [Screen Readers - OLP Power Apps - Content page]: Ensures buttons have discernible text. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yAuto; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; K4W; MAS 4.1.2; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517906 | Bug | Bug 1517906: [Screen Readers - OLP Power Apps - Content page]: Screen reader is announcing irrelevant information for progress bar, while navigating using browse mode | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Investigar como hacer para que NVDA no lea el progress bar. O que lea un texto que uno quiera como "completion bar" Comentario de Accessibility Team: @William Pena Announcing Edit, Clickable by the screen reader can be controlled by their verbose settings and it is expected behavior based on the verbose selection of the user. If Blank is removed, please assign the bug back to us and resolve. @Priyanka Mangla @David Payne WP Update (09/09/22): Ya revisé con NVDA y no está leyendo ni diciendo el Blank, por lo cual el bug se devolvuelve a ellos y se envia a revisión. | 2 - High | #REF! | #REF! | #REF!
1517907 | Bug | Bug 1517907: [Visual Requirements - OLP Power Apps - Content page]: Luminosity contrast ratio fails for the search control border. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.11; NewBaselineAssessment; RecID_8303 | Se realiza el ajuste de la sombra del search text, color anterior #8F8B8B, nuevo color #808080, validamos que cumpliera con el contrast ratio 3:1 | 3 - Medium | #REF! | #REF! | #REF!
1517928 | Bug | Bug 1517928: [Visual Requirement - OLP Power Apps - Content page]: Luminosity contrast ratio for the 'Marked as complete', 'Thanks for your feedback' text is less than 4.5:1. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.3; NewBaselineAssessment; RecID_8303 | Cambiar el color para que cumpla 4.5:1. Ojalá no negro Para este bug se debe trabajar con el Software Colour Contrast Analyser. Link para descargar software: https://www.tpgi.com/color-contrast-checker/ | 2 - High | #REF! | #REF! | #REF!
1517947 | Bug | Bug 1517947: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 400% zoom, Hamburger is not getting closed using ‘ESC’ key. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 | Revisar si es PowerApps dependency, ya que no se ha encontrado una función que implemente lo que el usuario oprima en el teclado. | 3 - Medium | #REF! | #REF! | #REF!
1517959 | Bug | Bug 1517959: [Screen Readers - OLP Power Apps - Content page]: Screen readers are not narrating state information for 'Home' control while navigating using shortcut key 'B'. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.1.2; NewBaselineAssessment; RecID_8303 | Bug reactivado. REVISAR Necesitan saber current state (si el usuario está en Home o en Browse). Posible solución. Label (visible) detrás del botón, con tab index 0. con text= "if(…. "Current state Home"). Onselect: select Thisitem.Button. FL: Sudheer va a pasar la solición. William porfa actualice el item en ADO (pedir la solución). WP: Se marcó como completado, ya que segú la reunión de hoy Sept 6 Dipankar mencionó que estos deberíamos de asignarlos de vuelta a ellos. | 2 - High | #REF! | #REF! | #REF!
1517961 | Bug | Bug 1517961: [Screen Readers - OLP Power Apps - Content page]: Screen reader not narrating correct state information for filter control, while navigating using browse mode | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Arreglar para sort y filter en ambas vistas y en Brwose y Content screen. | 2 - High | #REF! | #REF! | #REF!
1517966 | Bug | Bug 1517966: [Screen Readers - OLP Power Apps - Content page]: Screen readers are narrating unnecessary role for plain text. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Puede que nos molesten porque el screen reader lee "greater than" (>) | 2 - High | #REF! | #REF! | #REF!
1517968 | Bug | Bug 1517968: [Keyboard Navigation - OLP Power Apps - Content page]: Visual focus indicator is not clearly visible on 'cancel' button while navigating using keyboard Tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.7; NewBaselineAssessment; RecID_8303 | Realizamos el ajuste pertinente sobre el cancel del search text, ya se visualiza por completo cuando se utiliza el tabulador | 4 - Low | #REF! | #REF! | #REF!
1517970 | Bug | Bug 1517970: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 400% zoom, Keyboard focus is not moving to the menu items after expanding hamburger while navigating using tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517977 | Bug | Bug 1517977: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 200% zoom, Keyboard focus is not moving to the sort related controls upon activating 'Sort' button. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.4; NewBaselineAssessment; RecID_8303 | Accessibility team nos confirmó que es un product related bug. Existe la alternativa de SetFocus al botton de "Apply. | 2 - High | #REF! | #REF! | #REF!
1517978 | Bug | Bug 1517978: [Usable - OLP Power Apps - Content page]: Text is not aligned properly for the tiles present in the page and normal mode. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | William | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.2.7; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517980 | Bug | Bug 1517980: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 400% zoom, Keyboard focus indicator truncated for 'Filter' and 'Sort' buttons while navigating using tab or shift tab key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 | Se realiza el ajuste solicitado, los focus border ya no se contraponen | 4 - Low | #REF! | #REF! | #REF!
1517982 | Bug | Bug 1517982: [Screen Readers - OLP Power Apps - Content page]: Screen reader focus moving multiple times to buttons in the page while navigating using the down arrow key. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 |  | 3 - Medium | #REF! | #REF! | #REF!
1517987 | Bug | Bug 1517987: [Visual Requirement - OLP Power Apps - Content page]: After applying text spacing, text is getting overlapped. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.12; NewBaselineAssessment; RecID_8303 | Preguntamos por herramienta de text spacing. Seguimos pendientes para que nos pasen la que usan internamente. https://powerusers. .com/t5/Building-Power-Apps/NVDA-in-powerapps/m-p/621857#M196702 Después de una reunión con el dos ingenieros de Accessibility, Dipankar y Sudheer. Nos comentaron que si utilizamos la fuente Segoe UI, no deberiamos de tener problema con el tema de text spacing. | 2 - High | #REF! | #REF! | #REF!
1517990 | Bug | Bug 1517990: [Screen Readers- OLP Power Apps - Content page]: Screen reader does not announce any information after activating 'Back to your area' button. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Revisar si es una PowerApp dependency, ya que o se puede hacer focus a otra pantalla desde un botón localizado en un pantalla diferente. | 3 - Medium | #REF! | #REF! | #REF!
1517993 | Bug | Bug 1517993: [Screen Readers - OLP Power Apps - Content page]: Screen readers are not narrating the role for the pagination controls in the page. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.1.2; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1517996 | Bug | Bug 1517996: [Visual Requirement - OLP Power Apps - Content page]: Screen reader does not announce any information after activating 'Bookmark', 'Mark as complete' or 'Rate content' controls. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1518003 | Bug | Bug 1518003: [Screen Readers - OLP Power Apps - Content page]: Screen reader focus is moving to hidden content when we invoke 'Home' control. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.3.1; NewBaselineAssessment; RecID_8303 | Revisar, el botón anuncia el nombre del focus que se hace cuando se selecciona esta pantalla. | 3 - Medium | #REF! | #REF! | #REF!
1518005 | Bug | Bug 1518005: [Screen Readers - OLP Power Apps - Content page]: Screen Reader focus (NVDA/JAWS) is unnecessarily moving to the hidden control i.e. starting of the page upon invoking 'Filter' control while navigating in browse or VPC mode. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonScreenReaders; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.2.10; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1518011 | Bug | Bug 1518011: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus indicator is not visible on the entire page for tiles. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 2.4.7; NewBaselineAssessment; RecID_8303 | El focus borde esta implementado, y es visible | 2 - High | #REF! | #REF! | #REF!
1518029 | Bug | Bug 1518029: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 400% zoom, multiple scrollbars appear on the page. | New | Enrique Monsalve <v-monsalvee@ .com> | Pending w/ dependecy |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 | Bug reactivado. REVISAR Desactivamos desplazamiento vertical para algunos contenedores manteniendo funcionalidad de scroll, sin embargo las demas scroll bar se activan desde el navegador no desde la aplicación. FL: Sudheer va a pasar la solición. William porfa actualice el item en ADO (pedir la solución). | 2 - High | #REF! | #REF! | #REF!
1518044 | Bug | Bug 1518044: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 400% zoom, Screen reader (NVDA/JAWS) is not narrating the name of the few buttons present on the page. | New | Enrique Monsalve <v-monsalvee@ .com> | Si |  | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 | Se hizo cambio en Content y Browse screen. | 2 - High | #REF! | #REF! | #REF!
1518053 | Bug | Bug 1518053: [Supporting the platform - OLP Power Apps - Content page]: In High contrast Aquatic modes, Keyboard focus indicator is not displaying properly for 'Home', 'Browse' links. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.3.1; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1518059 | Bug | Bug 1518059: [Supporting the platform - OLP Power Apps - Content page]: In High contrast Aquatic Desert modes, Differentiation for selected/unselected tile is not able to differentiate. | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 4.3.1; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1518070 | Bug | Bug 1518070: [Supporting the platform - OLP Power Apps - Content page]: At 400% zoom mode, ensures every ARIA button, link and menu item has an accessible name | New | Enrique Monsalve <v-monsalvee@ .com> | Si | Mauricio | Completado | A11y-1STPARTY; A11yMAS; A11yMASP3; CommonBrowsers; HCL; HCL_OLP - MayJune FY22 New Update; MAS 1.4.10; NewBaselineAssessment; RecID_8303 |  | 2 - High | #REF! | #REF! | #REF!
1521753 | Bug | Bug 1521753: [Screen Readers - OLP Power Apps - Content page]: Screen reader focus is moving twice to 'bookmark' control in browse mode. | New | William Pena <v-wpena@ .com> | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1521759 | Bug | Bug 1521759: [Usable - OLP Power Apps - Content page]: Content is not getting displayed for tiles on the page. | New | William Pena <v-wpena@ .com> | Si |  | Completado |  | Este bug corresponde a datos del backend, más no al front end o accessibility. | 4 - Low | #REF! | #REF! | #REF!
1521793 | Bug | Bug 1521793: [Screen Readers - OLP Power Apps - Content page]: Ensures buttons have discernible text. | New | William Pena <v-wpena@ .com> | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521798 | [Screen Readers - OLP Power Apps - Content page]: Ensures buttons have discernible text. | Bug 1521798: [Supporting the platform - OLP Power Apps - Content page]: After resizing the page at 200% zoom, page content is not displaying properly. |  |  | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1521835 | [Keyboard Navigation - OLP Power Apps - Content page]: Drop down menu items are not displaying for 'Program' control upon receiving keyboard focus while navigating using arrow keys. | Bug 1521835: [Keyboard Navigation - OLP Power Apps - Content page]: Drop down menu items are not displaying for 'Program' control upon receiving keyboard focus while navigating using arrow keys. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521836 | [Supporting the platform - OLP Power Apps - Content page]: At 400% zoom mode, horizontal scrollbar appears on the page. | Bug 1521836: [Supporting the platform - OLP Power Apps - Content page]: At 400% zoom mode, horizontal scrollbar appears on the page. |  |  | Pending w/ dependecy |  | Completado |  | Mismo problema de las scrollbars del navegador en 400% zoom. | 3 - Medium | #REF! | #REF! | #REF!
1521837 | [Visual Requirements - OLP Power Apps - Content page]: After applying text spacing, few content present on the page is getting truncated. | Bug 1521837: [Visual Requirements - OLP Power Apps - Content page]: After applying text spacing, few content present on the page is getting truncated. |  |  | Si |  | Completado |  | Esperando guia del Team de Accessibility con la Text Spacing Tool. https://powerusers. .com/t5/Building-Power-Apps/NVDA-in-powerapps/m-p/621857#M196702 Después de una reunión con el dos ingenieros de Accessibility, Dipankar y Sudheer. Nos comentaron que si utilizamos la fuente Segoe UI, no deberiamos de tener problema con el tema de text spacing. | 3 - Medium | #REF! | #REF! | #REF!
1521838 | [Supporting the platform - OLP Power Apps - Content page]: At 400% Zoom mode, two vertical scroll bars appear on the page. | Bug 1521838: [Supporting the platform - OLP Power Apps - Content page]: At 400% Zoom mode, two vertical scroll bars appear on the page. |  |  | Pending w/ dependecy |  | Completado |  | Mismo problema de las scrollbars del navegador en 400% zoom. | 3 - Medium | #REF! | #REF! | #REF!
1521839 | [Supporting the platform - OLP Power Apps - Content page]: At 400% Zoom mode, few content present in the page getting truncated. | Bug 1521839: [Supporting the platform - OLP Power Apps - Content page]: At 400% Zoom mode, few content present in the page getting truncated. |  |  | Pending w/ dependecy |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521840 | [Supporting the platform - OLP Power Apps - Content page]: At 400% zoom mode, User is unable to select the drop-down menu item options for combo box while navigating using keyboard. | Bug 1521840: [Supporting the platform - OLP Power Apps - Content page]: At 400% zoom mode, User is unable to select the drop-down menu item options for combo box while navigating using keyboard. |  |  | Pending w/ dependecy |  | Completado |  | Revisar, porque la idea era no hacer la pantalla responsive. Nuestro comentario para team de accessibility: When addressing this bug, we found that a dropdown dynamic height is not a Power Apps function. This might be a product related bug, as from our research we didn't find any information on how to make the dropdown (expanded options) more visible or adjust its size according to the screen. Pending w/ dependency | 3 - Medium | #REF! | #REF! | #REF!
1521841 | [Supporting the platform - OLP Power Apps - Content page] In high contrast (Aquatic /Desert) mode additional chevron icon is observed in the header region. | Bug 1521841: [Supporting the platform - OLP Power Apps - Content page] In high contrast (Aquatic /Desert) mode additional chevron icon is observed in the header region. |  |  | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1521842 | [Supporting the platform - OLP Power Apps - Content page]: In high contrast (Aquatic /Desert) mode, Borders are not provided for the form fields present in the page. | Bug 1521842: [Supporting the platform - OLP Power Apps - Content page]: In high contrast (Aquatic /Desert) mode, Borders are not provided for the form fields present in the page. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521843 | [Supporting the platform - OLP Power Apps - Content page]: In high contrast (Aquatic /Desert) mode, Keyboard focus indicator is not displaying properly on 'Reset filters'. | Bug 1521843: [Supporting the platform - OLP Power Apps - Content page]: In high contrast (Aquatic /Desert) mode, Keyboard focus indicator is not displaying properly on 'Reset filters'. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521844 | [Screen Readers - OLP Power Apps - Content page]: Screen reader (NVDA/JAWS) focus is moving twice to 'Back to main page' control while navigating in browse mode. | Bug 1521844: [Screen Readers - OLP Power Apps - Content page]: Screen reader (NVDA/JAWS) focus is moving twice to 'Back to main page' control while navigating in browse mode. |  |  | Si |  | Completado |  | Revisar, si solo se debe mover al icono mas no al label. | 3 - Medium | #REF! | #REF! | #REF!
1521867 | [Screen Readers - OLP Power Apps - Content page]: Screen readers are narrating unnecessary 'Role' as button for 'Normal text', Present in the page, while navigating using down arrow key. | Bug 1521867: [Screen Readers - OLP Power Apps - Content page]: Screen readers are narrating unnecessary 'Role' as button for 'Normal text', Present in the page, while navigating using down arrow key. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521868 | [Keyboard Navigation- OLP Power Apps]: Keyboard focus moving to non-interactive text i.e., Area while navigating using keyboard tab key. | Bug 1521868: [Keyboard Navigation- OLP Power Apps]: Keyboard focus moving to non-interactive text i.e., Area while navigating using keyboard tab key. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521871 | [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard tab focus loss is observed after invoking 'Skip to main content'. | Bug 1521871: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard tab focus loss is observed after invoking 'Skip to main content'. |  |  | Pending w/ dependecy |  | Completado |  | Comentar en ADO: El comando de "Skip to ,ain Content" no es un control que nosotros configuremos, es algo del producto. | 3 - Medium | #REF! | #REF! | #REF!
1521879 | [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus is not on sequential order in the page, while navigating using keyboard tab key. | Bug 1521879: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus is not on sequential order in the page, while navigating using keyboard tab key. |  |  | Si |  | Completado |  | Revisar Propuesta con Federico | 3 - Medium | #REF! | #REF! | #REF!
1521880 | [Screen Readers - OLP Power Apps - Content page]: Table is not defined for the content which is visually appearing as table present on the page. | Bug 1521880: [Screen Readers - OLP Power Apps - Content page]: Table is not defined for the content which is visually appearing as table present on the page. |  |  | Pending w/ dependecy | William | Completado |  | En este bug utilizan la tecla "T" como shorcut para ir directo a la tabla, pero en nuestro caso usamos una Gallery. ¿No aplicaría este error? Limitación de Powerapps https://powerusers. .com/t5/Building-Power-Apps/NVDA-in-powerapps/m-p/621857#M196702 | 3 - Medium | #REF! | #REF! | #REF!
1521890 | [Screen Readers - OLP Power Apps - Content page]: Screen reader not narrating unavailable information for buttons (PP-1001) present in the page. | Bug 1521890: [Screen Readers - OLP Power Apps - Content page]: Screen reader not narrating unavailable information for buttons (PP-1001) present in the page. |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1521898 | [Screen Readers - OLP Power Apps]:'Form landmark' is not defined on the page. | Bug 1521898: [Screen Readers - OLP Power Apps]:'Form landmark' is not defined on the page. |  |  | Pending w/ dependecy | William | Completado |  | Comentar en ADO con link de PA limitations. https://docs. .com/en-us/power-apps/maker/canvas-apps/accessible-apps-limitations | 3 - Medium | #REF! | #REF! | #REF!
1521900 | [Screen Readers - OLP Power Apps]: Screen reader narrating extra verbose information for all the drop-down fields while navigating using short cut key 'f'. | Bug 1521900: [Screen Readers - OLP Power Apps]: Screen reader narrating extra verbose information for all the drop-down fields while navigating using short cut key 'f'. |  |  | Si |  | Completado |  | Discutir con Federico la solución. | 3 - Medium | #REF! | #REF! | #REF!
1521930 | [Supporting the platform- OLP Power Apps]: In High contrast Aquatic Desert modes, Differentiation for selected/unselected row is not able to differentiate | Bug 1521930: [Supporting the platform- OLP Power Apps]: In High contrast Aquatic Desert modes, Differentiation for selected/unselected row is not able to differentiate |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1522081 | [Visual Requirements - OLP Power Apps - Content page]: Luminosity contrast ratio fails edit or combo box fields border with its background. | Bug 1522081: [Visual Requirements - OLP Power Apps - Content page]: Luminosity contrast ratio fails edit or combo box fields border with its background. |  |  | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1522082 | [Supporting the platform - OLP Power Apps - Content page]: In High contrast Aquatic and Desert modes, Keyboard focus indicator is not visible on 'view other learning path' button while navigating using tab | Bug 1522082: [Supporting the platform - OLP Power Apps - Content page]: In High contrast Aquatic and Desert modes, Keyboard focus indicator is not visible on 'view other learning path' button while navigating using tab |  |  | Si |  | Completado |  |  | 2 - High | #REF! | #REF! | #REF!
1522083 | [Screen Readers - OLP Power Apps]: Screen reader (NVDA) does not announce any information after activating 'Go' button. | Bug 1522083: [Screen Readers - OLP Power Apps]: Screen reader (NVDA) does not announce any information after activating 'Go' button. |  |  | Si | William | Completado |  | Revisar este bug, ya que se probó con NVDA y si esta narrando información. | 3 - Medium | #REF! | #REF! | #REF!
1522085 | [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus loss is observed after invoking 'view other learning path' button while navigating using tab key | Bug 1522085: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus loss is observed after invoking 'view other learning path' button while navigating using tab key |  |  | Si | William | Completado | Revisar si es una PowerApp dependency, ya que o se puede hacer focus a otra pantalla desde un botón localizado en un pantalla diferente. | Discutir solución con Federico, Focus se hizo sobre otro elemento. | 3 - Medium | #REF! | #REF! | #REF!
1522094 | [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus indicator is not properly visible after invoking 'Go' button while navigating using tab key | Bug 1522094: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus indicator is not properly visible after invoking 'Go' button while navigating using tab key |  |  | Si | William | Completado |  | Discutir solución con Federico, Focus se hizo sobre otro elemento. | 3 - Medium | #REF! | #REF! | #REF!
1528136 |  | Bug 1528136: [Screen Readers - OLP Power Apps]: Screen reader (NVDA/JAWS) narrates 'Home' and 'Browse' button information twice while navigating using short cut key 'K'. |  |  | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1528235 |  | Bug 1528235: [Visual Requirements - OLP Power Apps - Content page]: Luminosity contrast ratio of the selected table data text with its background is less than 4.5:1. |  |  | Si |  | Completado |  |  | 3 - Medium | #REF! | #REF! | #REF!
1528636 |  | Bug 1528636: [Supporting the platform - OLP Power Apps - Content page]: In High contrast (Aquatic/Desert) modes, 'Browse' control is not visible properly. |  |  | Si |  | Completado |  | WP (12/09/12): Hacer comentario en ADO, ya que a la persona que revisó el app, no le aparece igual que a nosotros. En mi caso, cuando habilito los modos de Desert y Aquatic si puedo ver los bordr y el cambio de color en las letras de "Home" y "Browse". | 2 - High | #REF! | #REF! | #REF!
1531300 | Bug 1531300: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus order is not in sequential order after invoking 'Filter' control while navigating using keyboard tab key. | Bug 1531300: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus order is not in sequential order after invoking 'Filter' control while navigating using keyboard tab key. |  |  | Si |  | Completado |  |  | 4 - Low
1531353 | Bug 1531353: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of high contrast theme related dropdown controls with focus indicator fails to meet minimum required ratio. | Bug 1531353: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of high contrast theme related dropdown controls with focus indicator fails to meet minimum required ratio. |  |  | Si |  | Completado |  |  | 2 - High
1531357 | Bug 1531357: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of 'Browse' control with mouse hover is less than the minimum required ratio. | Bug 1531357: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of 'Browse' control with mouse hover is less than the minimum required ratio. |  |  | Si |  | Completado |  |  | 2 - High
1531362 | Bug 1531362: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of text i.e:'PP7296' in the table is less than the minimum required ratio. | Bug 1531362: [Visual Requirement - OLP Power Apps - Content page]: Luminosity ratio of text i.e:'PP7296' in the table is less than the minimum required ratio. |  |  | Si |  | Completado |  |  | 2 - High
1531367 | Bug 1531367: [Usable - OLP Power Apps - Content page]: Unnecessary text/icon is provided in the page. | Bug 1531367: [Usable - OLP Power Apps - Content page]: Unnecessary text/icon is provided in the page. |  |  | Si |  | Completado |  |  | 4 - Low
1531695 | Bug 1531395: [Screen readers - OLP Power Apps] : Generic page title is provided for all pages in the application. | Bug 1531395: [Screen readers - OLP Power Apps] : Generic page title is provided for all pages in the application. |  |  | Pending w/ dependecy |  | Completado |  |  | 2 - High
1531706 |  | Bug 1531706: [Keyboard Navigation - OLP Power Apps - Content page]: Keyboard focus moves out of the filter drop down control without closing it. |  |  | Pending w/ dependecy |  | Completado |  |  | 3 - Medium
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @William Pena (NEXTANT LLC) este debería quedar en ADO como "Active"? Reply: @Enrique Monsalve (NEXTANT LLC) en ADO está como Active pero para nosotros acá está en Hold porque nos pasaron una herramienta que no nos funciona. Estamos esperando a que nos pasen la herramienta que ellos usaron.
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @William Pena (NEXTANT LLC), este quedó como "Resolved" en ADO pero aquí esta diferente. Debería estar Completado?

## Accessibility Bugs 3rd Round
ID | Work Item Type | Title | Severity | State | Aprobado por Accessibility | Responsable | Status (Completado/En progreso/ No comenzado) | Tags | Comentarios | ADO Synced | ADO State | ADO Assigned to
1583715 | Bug | [Supporting the platform -Jan FY23 OLP My Choice Update - Access page]: In high contrast Desert mode, Profile and MCAPS related text is not displaying properly. | 2 - High | Resolved | No revisado | William | Completado
1583716 | Bug | [Usable -Jan FY23 OLP My Choice Update]: Visual differentiation is not provided for selected/un-selected controls after selecting 'My choice' control. | 2 - High | Resolved | No revisado | William | Completado | [5 empty] | Si
1583730 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: luminosity ratio of mark as complete and thanks for your feedback text fails to meet required ratio of 4.5:1. | 2 - High | Resolved | No revisado | Nicolás | Completado | [5 empty] | Reactivado
1583736 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update - Access page]: Heading <h1> is not defined in the page. | 2 - High | Resolved | No revisado | Mauricio | Completado | [5 empty] | No revisado
1583773 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update - Access page]: Screen reader (NVDA/JAWS) focus is not moving to the main landmark content present in the page while navigating using down arrow key in browse mode. | 2 - High | Resolved | No revisado | William | Completado | [5 empty] | Pending w/ dependecy
1583659 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Keyboard focus indicator is not visible on 'Request access' control while navigating using keyboard tab key. | 2 - High | Resolved | No revisado | William | Completado
1583709 | Bug | [Usable -Jan FY23 OLP My Choice Update - Access page]: High contrast modes are not applying to the few content present on the page. | 2 - High | Resolved | No revisado | William | Completado
1583793 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Luminosity ratio fails for 'Submit' button text fails to meet required ratio of 4.5:1. | 2 - High | Resolved | No revisado | Nicolás | Completado
1583797 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Luminosity contrast ratio of 'Modality' dropdown Text fails to meet the minimum required luminosity ratio of 3:1. | 2 - High | Resolved | No revisado | Nicolás | Completado
1583809 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update]: Label information is not mapped with the edit filed while navigating in focus mode. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1583714 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update]: Screen reader (NVDA/JAWS) not narrating state information for the 'All in path' control while navigating in focus mode. | 3 - Medium | Resolved | No revisado | William | Completado
1583776 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update - Access page]: Screen reader (JAWS) focus is moving to the hidden content after 'Account manager' control while navigating using down arrow key. | 3 - Medium | Resolved | No revisado | William | Completado
1583778 | Bug | [Keyboard Navigation -Jan FY23 OLP My Choice Update]: Keyboard focus is not landing on the triggered control after invoking back to main content Button. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1583783 | Bug | [Supporting the platform -Jan FY23 OLP My Choice Update - Content page]: After applying text spacing, 'Assigned to you' control text is getting truncated. | 3 - Medium | Resolved | No revisado | William | Completado
1583748 | Bug | [Keyboard Navigation -Jan FY23 OLP My Choice Update]: keyboard focus is unnecessarily moving to non-interactive 'modality' control. | 3 - Medium | Resolved | No revisado | Nicolás | Hold |  | Esperando feedback de Sudheer del team de accessibility.
1583767 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update - Access page]: Screen readers (NVDA/JAWS) narrate the role information twice topic 'B' button. | 3 - Medium | Resolved | No revisado | William | Completado
1583717 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Incorrect Tooltip is provided for 'Path' control present in the page. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1583719 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Luminosity ratio of focus indicator of 'Let's start' control with its background color is less than the required ratio of 3:1. | 3 - Medium | Resolved | No revisado | Nicolás | Completado
1583721 | Bug | [Keyboard Navigation -Jan FY23 OLP My Choice Update]: Keyboard focus loss is observed after invoking submit button while navigating using keyboard tab key. | 3 - Medium | Resolved | No revisado | Nicolás | Completado
1583726 | Bug | [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Tooltip is not provided for the 'Close(X)' control present inside the 'Search' control. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1583728 | Bug | [Supporting the platform -Jan FY23 OLP My Choice Update - Access page]: At 400% zoom mode, few content present on the page is getting truncated. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1583729 | Bug | [Supporting the platform -Jan FY23 OLP My Choice Update - Access page]: At 400% zoom mode, ensures aria-hidden elements do not contain focusable elements. | 3 - Medium | Resolved | No revisado | Nicolás | Completado
1583718 | Bug | [Screen Readers -Jan FY23 OLP My Choice Update]: Screen reader (NVDA/JAWS) not narrating additional information for the link(aka.ms/ONB) while navigating in focus mode. | 4 - Low | Resolved | No revisado | William | Completado
1583414 | Bug | [Keyboard Navigation -Jan FY23 OLP My Choice Update - Access page]: Keyboard tab focus loss is observed after invoking 'Skip to main content'. | 4 - Low | Pending w/ dependency | No revisado | William | Completado |  | Pending with dependency
1592691 | Bug | Bug 1592691: [Keyboard Navigation -Jan FY23 OLP My Choice Update - Access page]: Rating is automatically getting submitted without selecting star controls. | 2 - High | Resolved | No revisado | Mauricio | Completado
1592695 | Bug | Bug 1592695: [Functional - Jan FY23 OLP My Choice Update]: Form is getting submitted after activating 'Submit' button without filling required data. | 2 - High | Resolved | No revisado | Nicolás | Completado
1592714 | Bug | Bug 1592714: [Screen Readers -Jan FY23 OLP My Choice Update - Program Parameter (Role) Picker4]: Screen reader (NVDA) is not narrating table data information properly while navigating using tab or shift tab key. | 2 - High | Resolved | No revisado | Nicolás | Completado
1592717 | Bug | Bug 1592717: [Screen Readers -Jan FY23 OLP My Choice Update]: Screen reader (NVDA) not narrating state information even after we select a particular control while navigating in focus mode. | 2 - High | Resolved | No revisado | Mauricio | Completado
1592719 | Bug | Bug 1592719: [Keyboard Navigation - Jan FY23 OLP My Choice Update]: Keyboard focus is moving to non-interactive control ('*') while navigating using keyboard tab key. | 2 - High | Resolved | No revisado | Mauricio | Completado
1592703 | Bug | Bug 1592703: [Screen readers - Jan FY23 OLP My Choice Update]: Screen reader not narrating descriptive name for the left navigation controls while navigating in focus mode. | 2 - High | Resolved | No revisado | Nicolás | Completado
1592706 | Bug | Bug 1592706: [Screen Readers -Jan FY23 OLP My Choice Update - Program Parameter (Role) Picker4]: Visual label is not associated/mapped for combo/drop down box while navigating using screen reader. | 2 - High | Resolved | No revisado | William | Completado
1592707 | Bug | Bug 1592707: [Keyboard Navigation - Jan FY23 OLP My Choice Update]: Keyboard focus loss is observed after 'Back to browse' control while navigating using keyboard tab key. | 3 - Medium | Resolved | No revisado | William | Completado
1592722 | Bug | Bug 1592722: [Screen Readers -Jan FY23 OLP My Choice Update]: Screen reader (NVDA) not narrating state information for the 'header section controls while navigating in focus mode. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1592736 | Bug | Bug 1592736: [Usable -Jan FY23 OLP My Choice Update - Program Parameter (Role) Picker4]: Alternative way or shortcut key is not provided to access the control present after table while navigating using keyboard. | 3 - Medium | Resolved | No revisado | William | Completado
1592737 | Bug | Bug 1592737: [Keyboard Navigation - Jan FY23 OLP My Choice Update]: Keyboard tab focus loss is observed after invoking on 'Topic B' Button, while navigating using keyboard tab key. | 3 - Medium | Resolved | No revisado | Nicolás | Completado
1592748 | Bug | Bug 1592748: [Visual Requirements -Jan FY23 OLP My Choice Update - Program Parameter (Role) Picker4]: After applying text spacing 'program parameter (Role) picker 4' text is getting truncated. | 3 - Medium | Resolved | No revisado | William | Completado
1592699 | Bug | Bug 1592699: [Screen readers - Jan FY23 OLP My Choice Update]: Visually appearing as heading but programmatically not defined as heading. | 3 - Medium | Resolved | No revisado | Mauricio | Completado
1592676 | Bug | Bug 1592676: [Visual Requirements -Jan FY23 OLP My Choice Update - Access page]: Irrelevant tooltip is defined for Register button. | 3 - Medium | Resolved | No revisado | William | Completado

## Summary
Count of Title | Column Labels
Row Labels | 2 - High | 3 - Medium | 4 - Low | Grand Total
Resolved | 16 | 24 | 4 | 44
Closed | 7 | 2 | 1 | 10
Pending w/ dependency | 2 | 2 |  | 4
New | 2 | 9 | 2 | 13
Reactivated | 2 |  |  | 2
Grand Total | 29 | 37 | 7 | 73